**Wilmcote Neighbourhood Planning Group**

**Update no.9 February 2017**

In Update No 8 November 2016 it was explained that the Regulation 14 consultation needed to be rerun. This Regulation 14 consultation period ended 5th January 2017. Thank you to all who responded to this consultation.

The comments received enabled the next draft for formal submission to SDC to be prepared and the Neighbourhood Development Plan and associated documents have now been formally submitted to SDC.

You can view all documents on the parish website at <http://www.wilmcotepc.co.uk/parish-council/neighbourhood-development-plan/> look in section 4 ‘Submission Documents’.

SDC will now drive the process to the end. There may still be the need to do some work if any questions come back through these final steps. The final steps will be:

1. Formal consultation by SDC over the coming weeks.
2. Examination – an external examiner has been appointed and this is programmed to be conducted in April this year.
3. SDC consider Examiners report and identify any changes needed and prepare with us a final version of the Neighbourhood Development Plan.
4. SDC conduct a referendum in which you will be asked if you support the NDP, this is likely to be late summer.
5. SDC report sent to SDC cabinet for endorsement, then report to full council for adoption, this is likely to be autumn 2017.

If you have any questions you can contact the Parish Council Clerk, Liz Butterworth, either

by email: [lizbutterworth1@btinternet.com](mailto:lizbutterworth1@btinternet.com) or

by post to: The Clerk of the Parish Council, Liz Butterworth, Alne View, Pathlow, CV37 0ES.

**Contact Information**

Remember you can find more information about the Neighbourhood Development Plan on the Parish web site <http://www.wilmcotepc.co.uk/parish-council/neighbourhood-development-plan/> .